## DPDPA
Week | Day Range | Task | Description | Status | Evidence | Owner | Due Date | Notes
1 | Days 1-7 | Complete Learning Module 1: DPDPA 2023 Overview |  | Not Started
1 | Days 1-7 | Determine applicability: Data Fiduciary vs Data Processor |  | Not Started
1 | Days 1-7 | Map all digital personal data flows (collection to disposal) |  | Not Started
1 | Days 1-7 | Identify lawful basis for each processing activity |  | Not Started
1 | Days 1-7 | Classify data: personal, sensitive, children's data |  | Not Started
1 | Days 1-7 | Document data retention schedules and disposal procedures |  | Not Started
1 | Days 1-7 | Identify cross-border data transfers and mechanisms |  | Not Started
2 | Days 8-14 | Complete Learning Module 2: Consent & Rights Framework |  | Not Started
2 | Days 8-14 | Design consent mechanisms: free, informed, specific, unconditional |  | Not Started
2 | Days 8-14 | Implement consent withdrawal mechanism (as easy as giving) |  | Not Started
2 | Days 8-14 | Create clear privacy notices in plain language |  | Not Started
2 | Days 8-14 | Implement Data Principal rights: access, correction, erasure |  | Not Started
2 | Days 8-14 | Build grievance redressal mechanism with timelines |  | Not Started
2 | Days 8-14 | Design consent records management and audit trail |  | Not Started
3 | Days 15-21 | Complete Learning Module 3: Security & Breach Management |  | Not Started
3 | Days 15-21 | Implement reasonable security safeguards (technical & organizational) |  | Not Started
3 | Days 15-21 | Design data breach detection and assessment process |  | Not Started
3 | Days 15-21 | Implement 72-hour breach notification to DPB and affected persons |  | Not Started
3 | Days 15-21 | Appoint Data Protection Officer (DPO) if required |  | Not Started
3 | Days 15-21 | Conduct Data Protection Impact Assessments (DPIAs) for high-risk processing |  | Not Started
3 | Days 15-21 | Implement data protection by design and by default |  | Not Started
4 | Days 22-30+ | Complete Learning Module 4: Special Provisions & Ongoing Compliance |  | Not Started
4 | Days 22-30+ | Children's data: verifiable parental consent, age gating, no profiling |  | Not Started
4 | Days 22-30+ | Cross-border transfers: adequacy, SCCs, or exemptions |  | Not Started
4 | Days 22-30+ | Significant Data Fiduciary obligations: DPIA, auditor, DPO |  | Not Started
4 | Days 22-30+ | Implement data principal request portal and SLA tracking |  | Not Started
4 | Days 22-30+ | Vendor management: Data Processor contracts with DP clauses |  | Not Started
4 | Days 22-30+ | Ongoing: periodic audits, training, policy updates, DPB guidelines |  | Not Started