## GDPR
Week | Day Range | Task | Description | Status | Evidence | Owner | Due Date | Notes
1 | Days 1-7 | Complete Learning Module 1: GDPR Fundamentals & Scope |  | Not Started
1 | Days 1-7 | Determine applicability: Controller vs Processor, territorial scope |  | Not Started
1 | Days 1-7 | Map all personal data flows: collection → storage → processing → deletion |  | Not Started
1 | Days 1-7 | Identify lawful basis for each processing activity (Art. 6) |  | Not Started
1 | Days 1-7 | Classify data: personal, special category (Art. 9), children (Art. 8) |  | Not Started
1 | Days 1-7 | Document retention schedules and automated decision-making (Art. 22) |  | Not Started
1 | Days 1-7 | Identify international transfers and transfer mechanisms |  | Not Started
2 | Days 8-14 | Complete Learning Module 2: Data Subject Rights & Lawful Basis |  | Not Started
2 | Days 8-14 | Validate lawful basis for each processing activity (Art. 6/9) |  | Not Started
2 | Days 8-14 | Implement consent management: granular, informed, withdrawable |  | Not Started
2 | Days 8-14 | Build DSAR portal: access (Art. 15), rectification (16), erasure (17) |  | Not Started
2 | Days 8-14 | Implement restriction (18), portability (20), objection (21) |  | Not Started
2 | Days 8-14 | Design automated decision-making safeguards (Art. 22) |  | Not Started
2 | Days 8-14 | Create Records of Processing Activities (ROPA) per Art. 30 |  | Not Started
3 | Days 15-28 | Complete Learning Module 3: DPIA, DPO & Security |  | Not Started
3 | Days 15-28 | Conduct DPIAs for high-risk processing (Art. 35) with DPO consultation |  | Not Started
3 | Days 15-28 | Appoint DPO if required (Art. 37): public authority, large scale, special data |  | Not Started
3 | Days 15-28 | Implement technical/organizational measures (Art. 32): encryption, pseudonymization |  | Not Started
3 | Days 15-28 | Implement data protection by design (Art. 25) and by default |  | Not Started
3 | Days 15-28 | Establish breach detection, assessment, and 72-hour notification (Art. 33/34) |  | Not Started
3 | Days 15-28 | Implement processor contracts with Art. 28 clauses |  | Not Started
4 | Days 22-30+ | Complete Learning Module 4: Transfers, Accountability & Ongoing |  | Not Started
4 | Days 22-30+ | International transfers: adequacy, SCCs, BCRs, derogations (Art. 44-49) |  | Not Started
4 | Days 22-30+ | Maintain accountability: documentation, policies, training, audits |  | Not Started
4 | Days 22-30+ | Implement data protection by design (Art. 25) and by default |  | Not Started
4 | Days 22-30+ | Supervisory authority cooperation: lead SA, one-stop-shop (Art. 56) |  | Not Started
4 | Days 22-30+ | Codes of conduct (Art. 40) and certification mechanisms (Art. 42) |  | Not Started
4 | Days 22-30+ | Ongoing: periodic DPIAs, training, policy updates, EDPB guidelines |  | Not Started