## HIPAA
Week | Day Range | Task | Description | Status | Evidence | Owner | Due Date | Notes
1 | Days 1-7 | Complete Learning Module 1: HIPAA Fundamentals & Applicability |  | Not Started
1 | Days 1-7 | Determine Covered Entity vs Business Associate status |  | Not Started
1 | Days 1-7 | Assign Privacy Officer and Security Officer (required) |  | Not Started
1 | Days 1-7 | Identify all PHI/ePHI systems, flows, and repositories |  | Not Started
1 | Days 1-7 | Conduct comprehensive risk analysis (§164.308(a)(1)) |  | Not Started
1 | Days 1-7 | Document risk analysis methodology, findings, and risk ratings |  | Not Started
1 | Days 1-7 | Identify and document all Business Associates and BAAs needed |  | Not Started
2 | Days 8-14 | Complete Learning Module 2: Privacy Rule Implementation |  | Not Started
2 | Days 8-14 | Develop Notice of Privacy Practices (NPP) and distribution process |  | Not Started
2 | Days 8-14 | Implement patient rights: access, amendment, accounting, restrictions |  | Not Started
2 | Days 8-14 | Develop minimum necessary policies and workforce training |  | Not Started
2 | Days 8-14 | Implement uses/disclosures policies: TPO, authorization, required by law |  | Not Started
2 | Days 8-14 | Establish complaint process and breach notification procedures |  | Not Started
2 | Days 8-14 | Review and update Business Associate Agreements (BAAs) |  | Not Started
3 | Days 15-28 | Complete Learning Module 3: Security Rule - Admin & Physical |  | Not Started
3 | Days 15-28 | Administrative (§164.308): policies, workforce security, access mgmt |  | Not Started
3 | Days 15-28 | - Security awareness training, sanction policy, termination procedures |  | Not Started
3 | Days 15-28 | - Information access management, security incident procedures |  | Not Started
3 | Days 15-28 | Physical (§164.310): facility access, workstation/device security |  | Not Started
3 | Days 15-28 | - Facility access controls, workstation use, device/media controls |  | Not Started
3 | Days 15-28 | Develop contingency plan: data backup, DR, emergency mode operations |  | Not Started
3 | Days 15-28 | Implement evaluation process: periodic technical/non-technical eval |  | Not Started
4 | Days 22-30+ | Complete Learning Module 4: Technical Safeguards & Breach Response |  | Not Started
4 | Days 22-30+ | Technical Safeguards (§164.312): access control, audit controls, integrity |  | Not Started
4 | Days 22-30+ | - Unique user ID, emergency access, auto logoff, encryption/decryption |  | Not Started
4 | Days 22-30+ | - Audit controls: audit logs, review process, log integrity |  | Not Started
4 | Days 22-30+ | - Integrity: PHI integrity mechanisms, encryption at rest/transit |  | Not Started
4 | Days 22-30+ | - Person/entity authentication, transmission security (TLS, VPN) |  | Not Started
4 | Days 22-30+ | Breach Notification: risk assessment, 60-day notification, media notice |  | Not Started
4 | Days 22-30+ | Ongoing: periodic risk analysis, training, policy updates, BAAs review |  | Not Started